## AHP METHOD
AHP - Method
Comparison Matrix
Criteria | Quality | Price | Payment Flexibility | Order fulfillment | Time
Quality | 1 | 3 | 5 | 3 | 5
Price | 0.33333 | 1 | 1 | 1 | 1
Payment Flexibility | 0.2 | 1 | 1 | 1 | 1
Order fulfillment | 0.33333 | 1 | 1 | 1 | 1
Time | 0.2 | 1 | 1 | 1 | 1
Total | 2.0667 | 7 | 9 | 7 | 9
data have been standardised and are directional and Normalized
Criteria | Quality | Price | Payment Flexibility | Order fulfillment | Time | Total | Weight
Quality | 0.48387 | 0.42857 | 0.55556 | 0.42857 | 0.55556 | 2.4521 | 0.49042
Price | 0.16129 | 0.14286 | 0.11111 | 0.14286 | 0.11111 | 0.66923 | 0.13385
Payment Flexibility | 0.096774 | 0.14286 | 0.11111 | 0.14286 | 0.11111 | 0.60471 | 0.12094
Order fulfillment | 0.16129 | 0.14286 | 0.11111 | 0.14286 | 0.11111 | 0.66923 | 0.13385
Time | 0.096774 | 0.14286 | 0.11111 | 0.14286 | 0.11111 | 0.60471 | 0.12094
[6 empty] | 5 | 1
Consistancy
Criteria | Quality | Price | Payment Flexibility | Order fulfillment | Time | Total | Weight | WSV/CW
Quality | 0.49042 | 0.40154 | 0.60471 | 0.40154 | 0.60471 | 2.5029 | 0.49 | 5.108
Price | 0.16347 | 0.13385 | 0.12094 | 0.13385 | 0.12094 | 0.67305 | 0.13 | 5.1773
Payment Flexibility | 0.098085 | 0.13385 | 0.12094 | 0.13385 | 0.12094 | 0.60766 | 0.12 | 5.0638
Order fulfillment | 0.16347 | 0.13385 | 0.12094 | 0.13385 | 0.12094 | 0.67305 | 0.13 | 5.1773
Time | 0.098085 | 0.13385 | 0.12094 | 0.13385 | 0.12094 | 0.60766 | 0.12 | 5.0638
[7 empty] | λmax | 5.1181 | λmax - n | 0.11806
[9 empty] | n - 1 | 4
[9 empty] | CI | 0.029514
[8 empty] | RI: 1.12 | CR | 0.0263 | <0.1 | Acceptable

## AHP ANALYSIS
alternative suppliers | criteria
| Quality | Price | Payment Flexibility | Order fulfillment | Time
supplier A | 4.25 | 5 | 4 | 4.25 | 3
supplier B | 4.27 | 5 | 4.5 | 5 | 3
supplier C | 4.25 | 5 | 4.25 | 4 | 4
Total | 12.77 | 15 | 12.75 | 13.25 | 10
Normalized Data
alternative suppliers | criteria
| Quality | Price | Payment Flexibility | Order fulfillment | Time
supplier A | 0.33281 | 0.33333 | 0.31373 | 0.32075 | 0.3 | 0.32176
supplier B | 0.33438 | 0.33333 | 0.35294 | 0.37736 | 0.3 | 0.33459 | best one
supplier C | 0.33281 | 0.33333 | 0.33333 | 0.30189 | 0.4 | 0.33366
| 0.49 | 0.13 | 0.12 | 0.13 | 0.12

## activity planning
Index | Activities | pre-req | post-req | Beginning Date | Finishing Date | Duration (weeks) | Required Cost
A | collect necessary data in-house (i.e. past year inventory, invoices, etc) | start | B | 2023-01-01 | 2023-02-01 | 4
B | list known suppliers and find new potential ones | A | C | 2023-02-01 | 2023-02-15 | 2 | 25000
C | collect product information from suppliers (catalogue, offers, etc) | B | D,E,F,G,H,I,J,M | 2023-02-01 | 2023-02-28 | 3 | 10000
D | normalize price/product data and analyze against in-house data | C | E,I,K | 2023-03-01 | 2023-03-15 | 2 | 10000
E | vet supplier's reputation (financial stability, legal issues, known public records) | D | F,I,K | 2023-03-15 | 2023-03-30 | 2 | 15000
F | analyze and compare suppliers contracts legal framework (this includes warranties, RMA, payments, conflict resolution, etc.) | E | G,I,K | 2023-03-15 | 2023-03-30 | 2 | 5000
G | analyze and compare suppliers production capacity | F | H,I,K,L | 2023-03-15 | 2023-03-30 | 2 | 8000
H | analyze and compare suppliers logistics | G | I,K,L | 2023-03-15 | 2023-03-30 | 2 | 3000
I | select potential suppliers and star orders | E,F,G,H | J,K,L,M,N | 2023-04-01 | 2023-04-15 | 2 | 6000
J | analyze and compare suppliers personnel assigned to us | B | M,O,P,Q,R,S | 2023-04-01 | 2023-04-27 | 8 | 18000
K | project future growth and requirements and compare against projected supplier capacity and challenges | D | S | 2023-06-01 | 2023-06-30 | 4 | 10000
L | analyze suppliers production performance | I | O,S,N | 2023-07-01 | 2023-07-30 | 5 | 26000
M | analyze suppliers personnel interaction | B | O,P,S | 2023-08-07 | 2023-08-20 | 2 | 10000
N | evaluation/QC/QA of products | I | O,P,S | 2023-08-07 | 2023-09-30 | 8 | 3000
O | organize physical visits to suppliers production facilities | L | P,R,S | 2023-09-30 | 2023-10-31 | 4 | 30000
P | analyze and compare suppliers ability/willingness to develop/improve products according to our needs | L | Q,R,S | 2023-10-01 | 2023-11-01 | 4 | 24000
Q | evaluation of suppliers processes (legal, administrative, etc.) | M | R,S | 2023-10-01 | 2023-11-01 | 4 | 2000
R | identify and cultivate relationship between key personnel | M | S | 2023-11-01 | 2023-12-01 | 4 | 24000
S | identify and present critical issues with products/processes | I | T | 2023-11-01 | 2023-12-01 | 4 | 45000
T | renegotiate/close contracts based on performance/issues | T | end | 2023-12-01 | 2023-12-31 | 4 | 1000
[6 empty] | Total Amount | 295000

## GANTT
Index | Activity | Duratin (weeks) | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | october |  |  |  |  | november |  |  |  | desember
|  |  | 1th | 8th | 15th | 22th | 29th | 5th | 12th | 19th | 26th | 5th | 12th | 19th | 26th | 2th | 9th | 16th | 23th | 30th | 7th | 14th | 21th | 28th | 4th | 11th | 18th | 25th | 2th | 9th | 16th | 23th | 30th | 6th | 13th | 20th | 27th | 3th | 10th | 17th | 24th | 1th | 8th | 15th | 22th | 29th | 5th | 12th | 19th | 26th | 3th | 10th | 17th | 24th
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
1 | collect necessary data in-house (i.e. past year inventory, invoices, etc) | 4 | bar: January 1th 1 to January 29th 5
2 | list known suppliers and find new potential ones | 2 | bar: February 5th 6 to February 12th 7
3 | collect product information from suppliers (catalogue, offers, etc) | 3 | bar: February 12th 7 to February 26th 9
4 | normalize price/product data and analyze against in-house data | 2 | bar: March 5th 10 to March 12th 11
5 | vet supplier's reputation (financial stability, legal issues, known public records) | 2 | bar: March 19th 12 to March 26th 13
6 | analyze and compare suppliers contracts legal framework (this includes warranties, RMA, payments, conflict resolution, etc.) | 2 | bar: March 19th 12 to March 26th 13
7 | analyze and compare suppliers production capacity | 2 | bar: March 19th 12 to March 26th 13
8 | analyze and compare suppliers logistics | 2 | bar: March 19th 12 to March 26th 13
9 | select potential suppliers and star orders | 2 | bar: April 2th 14 to April 9th 15
10 | analyze and compare suppliers personnel assigned to us | 8 | bar: April 2th 14 to May 21th 21
11 | project future growth and requirements and compare against projected supplier capacity and challenges | 4 | bar: June 4th 23 to June 25th 26
12 | analyze suppliers production performance | 5 | bar: July 2th 27 to July 30th 31
13 | analyze suppliers personnel interaction | 2 | bar: August 6th 32 to August 13th 33
14 | evaluation/QC/QA of products | 8 | bar: August 6th 32 to September 24th 39
15 | organize physical visits to suppliers production facilities | 4 | bar: october 1th 40 to october 29th 44
16 | analyze and compare suppliers ability/willingness to develop/improve products according to our needs | 4 | bar: october 1th 40 to october 29th 44
17 | evaluation of suppliers processes (legal, administrative, etc.) | 4 | bar: october 1th 40 to october 29th 44
18 | identify and cultivate relationship between key personnel | 4 | bar: november 5th 45 to november 26th 48
19 | identify and present critical issues with products/processes | 4 | bar: november 5th 45 to november 26th 48
20 | renegotiate/close contracts based on performance/issues | 4 | bar: desember 3th 49 to desember 24th 52

## Probability Calculation
Index | Activities | optimistic duration Do | most likely duration Dm | pessimistic duration Dp | Variance (sigma) | Expected Duration(Te) | Percentage used for Do | Percentage used for Dp | duration (Weeks)
A | collect necessary data in-house (i.e. past year inventory, invoices, etc) | 8 | 20 | 28 | 11.1111 | 19 | 0.6 | 0.4 | 4
B | list known suppliers and find new potential ones | 4 | 10 | 14 | 2.7778 | 9 |  |  | 2
C | collect product information from suppliers (catalogue, offers, etc) | 6 | 15 | 21 | 6.25 | 14 |  |  | 3
D | normalize price/product data and analyze against in-house data | 4 | 10 | 14 | 2.7778 | 9 |  |  | 2
E | vet supplier's reputation (financial stability, legal issues, known public records) | 4 | 10 | 14 | 2.7778 | 9 |  |  | 2
F | analyze and compare suppliers contracts legal framework (this includes warranties, RMA, payments, conflict resolution, etc.) | 4 | 10 | 14 | 2.7778 | 9 |  |  | 2
G | analyze and compare suppliers production capacity | 4 | 10 | 14 | 2.7778 | 9 |  |  | 2
H | analyze and compare suppliers logistics | 4 | 10 | 14 | 2.7778 | 9 |  |  | 2
I | select potential suppliers and star orders | 4 | 10 | 14 | 2.7778 | 9 |  |  | 2
J | analyze and compare suppliers personnel assigned to us | 16 | 40 | 56 | 44.4444 | 38 |  |  | 8
K | project future growth and requirements and compare against projected supplier capacity and challenges | 8 | 20 | 28 | 11.1111 | 19 |  |  | 4
L | analyze suppliers production performance | 10 | 25 | 35 | 17.3611 | 24 |  |  | 5
M | analyze suppliers personnel interaction | 4 | 10 | 14 | 2.7778 | 9 |  |  | 2
N | evaluation/QC/QA of products | 16 | 40 | 56 | 44.4444 | 38 |  |  | 8
O | organize physical visits to suppliers production facilities | 8 | 20 | 28 | 11.1111 | 19 |  |  | 4
P | analyze and compare suppliers ability/willingness to develop/improve products according to our needs | 8 | 20 | 28 | 11.1111 | 19 |  |  | 4
Q | evaluation of suppliers processes (legal, administrative, etc.) | 8 | 20 | 28 | 11.1111 | 19 |  |  | 4
R | identify and cultivate relationship between key personnel | 8 | 20 | 28 | 11.1111 | 19 |  |  | 4
S | identify and present critical issues with products/processes | 8 | 20 | 28 | 11.1111 | 19 |  |  | 4
T | renegotiate/close contracts based on performance/issues | 8 | 20 | 28 | 11.1111 | 19 |  |  | 4
| Sum of Variance | == |  |  | 223.6111
| Standard deviation | == |  |  | 14.9536
| Sum of Expected Durations | == |  |  | 338
| Checking Project Time (2 weeks before the date) | == |  |  | 14
| Z-Score | == |  |  | -0.93623

## EVA Analaysis
Index | Activities | Duration (weeks) | Required Cost | Activities | PV = BCWS | AC = ACWP | EV = BCWP | CPI=EV / AC | CV = EV - AC | SPI= EV/PV | SV = EV - PV | EAC
A | collect necessary data in-house (i.e. past year inventory, invoices, etc) | 4 | 20000 | WP1 | 20000 | 20000 | 20000 | 1 | 0 | 1 | 0
B | list known suppliers and find new potential ones | 2 | 25000 | WP2 | 26250 | 28875 | 25000 | 0.8658 | -3875 | 0.95238 | -1250
C | collect product information from suppliers (catalogue, offers, etc) | 3 | 10000 | WP3 | 9500 | 8550 | 10000 | 1.1696 | 1450 | 1.0526 | 500
D | normalize price/product data and analyze against in-house data | 2 | 10000 | WP4 | 10200 | 10608 | 10000 | 0.94268 | -608 | 0.98039 | -200
E | vet supplier's reputation (financial stability, legal issues, known public records) | 2 | 15000 |  | 65950 | 68033 | 65000 | 0.95542 | -3033 | 0.9856 | -950 | 307446.2333
F | analyze and compare suppliers contracts legal framework (this includes warranties, RMA, payments, conflict resolution, etc.) | 2 | 5000
G | analyze and compare suppliers production capacity | 2 | 8000 |  | 20000 | 20000 | 20000
H | analyze and compare suppliers logistics | 2 | 3000 |  | 46250 | 48875 | 45000
I | select potential suppliers and star orders | 2 | 6000 |  | 55750 | 57425 | 55000
J | analyze and compare suppliers personnel assigned to us | 8 | 18000 |  | 65950 | 68033 | 65000
K | project future growth and requirements and compare against projected supplier capacity and challenges | 4 | 10000
L | analyze suppliers production performance | 5 | 26000
M | analyze suppliers personnel interaction | 2 | 10000
N | evaluation/QC/QA of products | 8 | 3000
O | organize physical visits to suppliers production facilities | 4 | 30000
P | analyze and compare suppliers ability/willingness to develop/improve products according to our needs | 4 | 24000
Q | evaluation of suppliers processes (legal, administrative, etc.) | 4 | 2000
R | identify and cultivate relationship between key personnel | 4 | 24000
S | identify and present critical issues with products/processes | 4 | 45000
T | renegotiate/close contracts based on performance/issues | 4 | 1000
295000